## Cover Page (T)
Grum 2022 Drill Planning
Planned ID | Order | Hole-ID | Zone | Date Started | Date Completed | Drill Status | Pad Status | Drill ID | Easting (proposed) | Northing (proposed) | Elevation (m) | Azimuth | Dip | Total Depth | Final Easting | Final Northing | Final Elevation | Final Depth (m) | Casing in/out | DH Survey | RTK (collar survey) | Collar + tag? | Plugged? | Logged | Sampled | Reclaimed
22GMET01 |  |  | Grum |  |  | Cancelled | Cancelled | Drill 1 | 592229.0419 | 6905486.9725 | 1227.803 | 130 | 75 | 35 |  |  |  |  | Out | Y | Y | Y | Y | Y | N | Y
22GMET02 | 4 | MG-22-G04 | Grum | 2022-11-03 | 2022-11-04 | Complete | Complete | Drill 1 | 592138.3369 | 6905421.1787 | 1227 | 130 | 80 | 100 | 592142 | 6905422 | 1228 | 102 | Out | Y | Y | Y | Y | Y | N | Y
22GMET03 | 3 | MG-22-G03 | Grum | 2022-10-30 | 2022-11-02 | Complete | Complete | Drill 1 | 592104.2576 | 6905334.5679 | 1227.5774 | 140 | 85 | 290 | 592104 | 6905337 | 1223 | 292 | Out | Y | Y | Y | Y | Y | N | Y
22GMET04 | 2 | MG-22-G02 | Grum | 2022-10-26 | 2022-10-30 | Complete | Complete | Drill 1 | 592020.15 | 6905246 | 1228.7406 | 130 | 65 | 280 | 592020 | 6905247 | 1222 | 289 | Out | Y | Y | Y | Y | Y | N | Y
22GMET05 | 1 | MG-22-G01 | Grum | 2022-10-22 | 2022-10-26 | Complete | Complete | Drill 1 | 592020.1494 | 6905246.6311 | 1228.7406 | 70 | 85 | 280 | 592020 | 6905247 | 1222 | 282 | Out | Y | Y | Y | Y | Y | N | Y
22GMET06 | 6 | MG-22-G06 | Grum | 2022-11-08 | 2022-11-11 | Complete | Complete | Drill 1 | 592338.2233 | 6904697.0553 | 1264.8004 | 65 | 85 | 190 | 592337 | 6904699 | 1300 | 189 | Out | Y | Y | Y | Y | Y | N | Y
22GMET07 | 7 | MG-22-G08 | Grum | 2022-11-14 | 2022-11-16 | Complete | Complete | Drill 1 | 592383.5196 | 6904657.2867 | 1262.2061 | 45 | 85 | 180 | 592381 | 6904657 | 1252 | 180 | Out | Y | Y | Y | Y | Y | N | Y
22GMET08 | 8 | MG-22-G07 | Grum | 2022-11-11 | 2022-11-13 | Complete | Complete | Drill 1 | 592431.5149 | 6904618.274 | 1254.833 | 45 | 85 | 135 | 592433 | 6904622 | 1234 | 135 | Out | Y | Y | Y | Y | Y | N | Y
22GMET09 | 5 | MG-22-G05 | Grum | 2022-11-04 | 2022-11-05 | Complete | Complete | Drill 1 | 592138.34 | 6905421.18 | 1227 | 35 | 60 | 80 | 592145 | 6905421 | 1228 | 82

## Downhole Survey Data (R)
Project Name | Drillhole Name | Unit of Measure | Measured Depth (m) | Dip | Azimuth | Gravity TF (Deg) | Magnetic TF (Deg) | Gravity Total (G) | Mag Total (nT) | Mag Dip (Deg) | ToolTemp (Deg C) | Measurement Date (YYYY_MM_DD_hh_mm_ss) | Firmware version | Software version | Tool SN | Tool Name | Notes | Direction | Operator | Rig | Latitude(DD) | Longitude(DD) | Location Input | GravX (G) | GravY (G) | GravZ (G) | MagX (nT) | MagY (nT) | MagZ (nT) | Battery (V) | QAQC Status | Mag Total Reference (nT) | Mag Dip Reference (Deg) | Reference Source
GRUM | MG-22-G08 | Metres | 24 | -86.1376 | 25.5495 | 6.2716 | 42.4478 | 1.0037 | 57540.6804 | 77.7546 | 1 | 2022_11_15_01_35_23 | v1.00 | 6.2.3008 | 5916 | EZ-TRAC |  | IN | COLIN | 1 | 62.262 | -133.2208 | Device | -0.067204 | 0.0073857 | 1.0014 | 6579.9915 | -6018.4337 | 56845.5106 | OK | Passed | 56688.25 | 77.3536 | Auto
GRUM | MG-22-G08 | Metres | 48 | -86.4312 | 25.5077 | 342.3985 | 17.3973 | 1.002 | 57356.8267 | 77.7105 | 6.5 | 2022_11_15_10_40_33 | v1.00 | 6.2.3008 | 5916 | EZ-TRAC |  | IN | CLINT | # 1 | 62.262 | -133.2208 | Device | -0.059452 | -0.018861 | 1.0001 | 8746.8718 | -2740.6458 | 56619.6667 | OK | Passed | 56688.25 | 77.3536 | Auto
GRUM | MG-22-G08 | Metres | 75 | -86.4788 | 24.7562 | 312.3463 | 346.2498 | 1.0018 | 57795.0342 | 77.7672 | 8.5 | 2022_11_15_17_14_43 | v1.00 | 6.2.3008 | 5916 | EZ-TRAC |  | IN | CLINT | # 1 | 62.262 | -133.2208 | Device | -0.041445 | -0.045474 | 0.99988 | 8929.9884 | 2185.192 | 57059.1467 | OK | Failed - MT | 56688.25 | 77.3536 | Auto
GRUM | MG-22-G08 | Metres | 99 | -86.1577 | 26.2378 | 261.6341 | 298.7142 | 1.0017 | 57317.917 | 77.8013 | 12 | 2022_11_16_00_03_45 | v1.00 | 6.2.3008 | 5916 | EZ-TRAC |  | IN | COLIN | 1 | 62.262 | -133.2208 | Device | 0.0097662 | -0.06641 | 0.99945 | 4266.6178 | 7788.5613 | 56625.7706 | OK | Passed | 56688.25 | 77.3536 | Auto
GRUM | MG-22-G08 | Metres | 124 | -86.1399 | 29.4426 | 262.4122 | 303.2156 | 1.0025 | 57004.0342 | 77.3308 | 2 | 2022_11_16_06_31_58 | v1.00 | 6.2.3008 | 5916 | EZ-TRAC |  | IN | COLIN | 1 | 62.262 | -133.2208 | Device | 0.0089117 | -0.066899 | 1.0002 | 5151.6816 | 7867.9119 | 56222.914 | OK | Passed | 56688.25 | 77.3536 | Auto
GRUM | MG-22-G08 | Metres | 150 | -85.7082 | 33.2916 | 210.9078 | 255.4342 | 1.002 | 58549.1731 | 74.8027 | 6 | 2022_11_16_13_47_11 | v1.00 | 6.2.3008 | 5916 | EZ-TRAC |  | IN | CLINT | # 1 | 62.262 | -133.2208 | Device | 0.064335 | -0.038516 | 0.99915 | -3021.4246 | 11627.907 | 57303.3022 | OK | Failed - MD MT | 56688.25 | 77.3536 | Auto
GRUM | MG-22-G08 | Metres | 174 | -85.9444 | 35.1946 | 258.3223 | 307.5823 | 1.002 | 56600.0162 | 77.4881 | 4 | 2022_11_16_19_01_14 | v1.00 | 6.2.3008 | 5916 | EZ-TRAC |  | IN | CLINT | # 1 | 62.262 | -133.2208 | Device | 0.014344 | -0.069401 | 0.99951 | 5688.8238 | 7391.8086 | 55826.1613 | OK | Passed | 56688.25 | 77.3536 | Auto

## Geotechnical (E)
From (m) | To (m) | Recovery (m) | RQD (m) | Strength (1-5) | HCL Reactivity (1-5) | Weathering (1-5) | Hardness (1-5) | Fracture Frequency | Joint Sets | Comments
0 | 12 | 0.6 | 0 |  | 3 - Moderate Reaction | 5 - Completely Weathered |  |  |  | Overburnden, poor recovery
12 | 15 | 2.05 | 0 |  | 4 - Strong Reaction | 5 - Completely Weathered |  |  |  | Till
15 | 18 | 1.15 | 0 |  | 4 - Strong Reaction | 5 - Completely Weathered |  |  |  | Till
18 | 21 | 2.98 | 0 |  | 4 - Strong Reaction | 5 - Completely Weathered |  |  |  | Till
21 | 24 | 1 | 0 |  | 3 - Moderate Reaction | 3 - Medium Weathered | 3 - Medium | 150
24 | 27 | 2 | 0 |  | 3 - Moderate Reaction | 1 - Unweathered | 3 - Medium | 150
27 | 30 | 2.2 | 0.12 |  | 3 - Moderate Reaction | 1 - Unweathered | 3 - Medium | 150
30 | 33 | 2 | 0 |  | 1 - No Reaction | 1 - Unweathered | 2 - Soft | 150
33 | 36 | 2.33 | 0 |  | 1 - No Reaction | 1 - Unweathered | 2 - Soft | 150
36 | 39 | 2.45 | 0 |  | 1 - No Reaction | 1 - Unweathered | 2 - Soft | 150 |  | 30 cm chunk of quartz = very hard
39 | 42 | 2.25 | 0 |  | 1 - No Reaction | 1 - Unweathered | 2 - Soft | 150
42 | 45 | 2.2 | 0.34 |  | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 150
45 | 48 | 2.71 | 0.25 |  | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 150
48 | 51 | 2.22 | 0.1 |  | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 150
51 | 54 | 2.65 | 0.12 |  | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 150
54 | 57 | 1.97 | 0.14 |  | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 150
57 | 60 | 2.22 | 0.51 |  | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 125
60 | 63 | 2.56 | 0.42 |  | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 110
63 | 66 | 2.73 | 0.88 |  | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 57
66 | 69 | 2.8 | 0.85 |  | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 55
69 | 72 | 2.96 | 0.76 |  | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 80
72 | 75 | 2.42 | 0.88 |  | 1 - No Reaction | 1 - Unweathered | 5 - Very Hard | 65
75 | 78 | 2.7 | 1.02 |  | 1 - No Reaction | 1 - Unweathered | 4 - Hard | 60
78 | 81 | 3 | 1.37 |  | 1 - No Reaction | 1 - Unweathered | 4 - Hard | 47
81 | 84 | 2.54 | 1.1 |  | 1 - No Reaction | 1 - Unweathered | 5 - Very Hard | 47
84 | 87 | 2.22 | 1.6 |  | 1 - No Reaction | 1 - Unweathered | 5 - Very Hard | 28
87 | 90 | 3 | 1.18 |  | 1 - No Reaction | 1 - Unweathered | 5 - Very Hard | 42
90 | 93 | 3 | 2.09 |  | 1 - No Reaction | 1 - Unweathered | 5 - Very Hard | 29
93 | 96 | 2.82 | 1.74 |  | 1 - No Reaction | 1 - Unweathered | 5 - Very Hard | 31
96 | 99 | 3 | 2.13 |  | 1 - No Reaction | 1 - Unweathered | 4 - Hard | 25
99 | 102 | 2.4 | 1.97 |  | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 18
102 | 105 | 2.82 | 2.04 |  | 1 - No Reaction | 1 - Unweathered | 4 - Hard | 21
105 | 108 | 3.2 | 1.63 |  | 1 - No Reaction | 1 - Unweathered | 4 - Hard | 33
108 | 111 | 2.65 | 1.05 |  | 1 - No Reaction | 1 - Unweathered | 5 - Very Hard | 48
111 | 114 | 2.95 | 2.19 |  | 1 - No Reaction | 1 - Unweathered | 4 - Hard | 24
114 | 117 | 2.91 | 2.03 |  | 3 - Moderate Reaction | 1 - Unweathered | 2 - Soft | 26
117 | 120 | 3.11 | 2.18 | 3 - Moderate | 3 - Moderate Reaction | 1 - Unweathered | 3 - Medium | 30
120 | 123 | 2.94 | 2.24 | 4 - Hard | 3 - Moderate Reaction | 1 - Unweathered | 3 - Medium | 23
123 | 126 | 3.1 | 2.47 | 3 - Moderate | 3 - Moderate Reaction | 1 - Unweathered | 3 - Medium | 25
126 | 129 | 2.99 | 2.33 | 3 - Moderate | 3 - Moderate Reaction | 1 - Unweathered | 3 - Medium | 18
129 | 132 | 2.84 | 2.15 | 3 - Moderate | 3 - Moderate Reaction | 1 - Unweathered | 3 - Medium | 21
132 | 135 | 3 | 2.33 | 3 - Moderate | 3 - Moderate Reaction | 1 - Unweathered | 3 - Medium | 22
135 | 138 | 2.92 | 2.3 | 3 - Moderate | 3 - Moderate Reaction | 1 - Unweathered | 3 - Medium | 27
138 | 141 | 2.94 | 1.75 | 3 - Moderate | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 24
141 | 144 | 2.91 | 1.86 |  | 1 - No Reaction | 1 - Unweathered | 4 - Hard | 28
144 | 147 | 3 | 2.56 |  | 1 - No Reaction | 1 - Unweathered | 4 - Hard | 22
147 | 150 | 2.92 | 2.27 |  | 1 - No Reaction | 1 - Unweathered | 4 - Hard | 15
150 | 153 | 2.61 | 1.92 |  | 1 - No Reaction | 1 - Unweathered | 4 - Hard | 24
153 | 156 | 3 | 2.67 |  | 1 - No Reaction | 1 - Unweathered | 4 - Hard | 17
156 | 159 | 3.14 | 2.66 | 4 - Hard | 1 - No Reaction | 1 - Unweathered | 5 - Very Hard | 15
159 | 162 | 2.95 | 2.61 | 4 - Hard | 1 - No Reaction | 1 - Unweathered | 5 - Very Hard | 14
162 | 165 | 3 | 2.37 | 4 - Hard | 1 - No Reaction | 1 - Unweathered | 5 - Very Hard | 20
165 | 168 | 2.97 | 2.43 | 4 - Hard | 1 - No Reaction | 1 - Unweathered | 5 - Very Hard | 20
168 | 171 | 2.95 | 1.49 | 3 - Moderate | 1 - No Reaction | 1 - Unweathered | 4 - Hard | 28
171 | 174 | 3 | 1.72 | 3 - Moderate | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 50
174 | 177 | 3 | 0.93 | 3 - Moderate | 1 - No Reaction | 1 - Unweathered | 3 - Medium | 35
177 | 180 | 1.95 | 0.48 | 2 - Soft | 1 - No Reaction | 1 - Unweathered | 2 - Soft | 80

## Magnetic Susceptibility
Depth (m) | Magnetic Susceptibility (10^-3 SI)
1 | -
2 | -
3 | -
4 | -
5 | -
6 | -
7 | -
8 | -
9 | -
10 | -
11 | -
12 | 0.527
13 | 0.451
14 | 0.547
15 | 0.617
16 | 0.652
17 | 1.57
18 | 0.714
19 | 0.65
20 | 0.786
21 | 0.465
22 | 0.247
23 | 0.142
24 | 0.056
25 | 0.612
26 | 1.11
27 | 1.6
28 | 0.257
29 | 0.184
30 | 0.639
31 | 0.36
32 | 0.341
33 | 1.21
34 | 1.09
35 | 0.5
36 | 1.48
37 | 0.141
38 | 0.013
39 | 0.22
40 | 0.33
41 | 0.36
42 | 0.504
43 | 0.158
44 | 0.18
45 | 0.165
46 | 0.71
47 | 0.356
48 | 0.437
49 | 0.407
50 | 0.538
51 | 0.297
52 | 0.416
53 | 0.574
54 | 0.156
55 | 0.332
56 | 0.31
57 | 0.516
58 | 0.312
59 | 0.814
60 | 0.351
61 | 0.475
62 | 0.484
63 | 0.676
64 | 0.364
65 | 0.456
66 | 0.485
67 | 0.71
68 | 0.589
69 | 0.373
70 | 0.452
71 | 0.713
72 | 0.399
73 | 3.05
74 | 347
75 | 1.33
76 | 4.96
77 | 5.17
78 | 6.46
79 | 0.654
80 | 3.98
81 | 3.42
82 | 13.8
83 | 2.87
84 | 12.3
85 | 0.63
86 | 0.777
87 | 0.783
88 | 0.459
89 | 0.401
90 | 0.439
91 | 0.748
92 | 0.299
93 | 0.408
94 | 0.325
95 | 70.9
96 | 0.297
97 | 15
98 | 0.513
99 | 0.574
100 | 3.2
101 | 1.22
102 | 0.895
103 | 0.327
104 | 0.336
105 | 0.556
106 | 1.05
107 | 0.788
108 | 0.509
109 | 0.767
110 | 0.593
111 | 0.582
112 | 19.9
113 | 3.1
114 | 1.47
115 | 0.456
116 | 1.66
117 | 0.71
118 | 0.831
119 | 2.06
120 | 0.534
121 | 1.09
122 | 0.798
123 | 0.652
124 | 0.99
125 | 1.44
126 | 0.651
127 | 1.13
128 | 1.52
129 | 0.681
130 | 0.77
131 | 1.3
132 | 0.886
133 | 1.57
134 | 2.65
135 | 2.16
136 | 3.11
137 | 8.09
138 | 10.9
139 | 1.37
140 | 1.01
141 | 1.02
142 | 0.355
143 | 0.334
144 | 1.2
145 | 1.06
146 | 153
147 | 184
148 | 61.5
149 | 113
150 | 21.8
151 | 3.45
152 | 1.63
153 | 169
154 | 20.5
155 | 13.7
156 | 8.92
157 | 245
158 | 32.8
159 | 201
160 | 30.9
161 | 55
162 | 15
163 | 34.8
164 | 13.4
165 | 12.8
166 | 27.2
167 | 1.96
168 | 73.4
169 | 15.1
170 | 8.16
171 | 2
172 | 1.3
173 | 0.662
174 | 0.277
175 | 0.334
176 | 0.256
177 | 0.29
178 | 0.495
179 | 0.069
180 | 0.496

## Box Log
Box | From (m) | To (m)
1 | 0 | 15
2 | 15 | 19.93
3 | 19.93 | 24.4
4 | 24.4 | 28
5 | 28 | 31.09
6 | 31.09 | 34.48
7 | 34.48 | 37.4
8 | 37.4 | 40.51
9 | 40.51 | 43.06
10 | 43.06 | 45.91
11 | 45.91 | 49
12 | 49 | 52.36
13 | 52.36 | 55.37
14 | 55.37 | 59.05
15 | 59.05 | 62.64
16 | 62.64 | 65.82
17 | 65.82 | 68.96
18 | 68.96 | 71.66
19 | 71.66 | 74.82
20 | 74.82 | 77.69
21 | 77.69 | 80.64
22 | 80.64 | 83.75
23 | 83.75 | 86.7
24 | 86.7 | 89.3
25 | 89.3 | 92.27
26 | 92.27 | 95.38
27 | 95.38 | 98.15
28 | 98.15 | 101.23
29 |  | 104.5
30 | 104.5 | 107.32
31 | 107.32 | 110.05
32 | 110.05 | 113.2
33 | 113.2 | 116.29
34 | 116.29 | 119.47
35 | 119.47 | 122.74
36 | 122.74 | 125.73
37 | 125.73 | 128.9
38 | 128.9 | 132.21
39 | 132.21 | 135.41
40 | 135.41 | 138.77
41 | 138.77 | 142
42 | 142 | 145.02
43 | 145.02 | 148.12
44 | 148.12 | 151.46
45 | 151.46 | 155.03
46 | 155.03 | 158.18
47 | 158.18 | 161.59
48 | 161.59 | 164.83
49 | 164.83 | 168
50 | 168 | 171.18
51 | 171.18 | 174.13
52 | 174.13 | 177.1
53 | 177.1 | 180

## Density
From (m) | To (m) | Lithology | Core Length (cm) | Core Size (cm) | Weight - Air (g) | Weight - Water (g) | Volume | Density | SG
74.67 | 74.82 |  | 15 | 6.35 | 1690 | 1230 | 475.0379 | 3.5576 | 3.6739
91.54 | 91.65 |  | 11 | 6.35 | 1400 | 1045 | 348.3611 | 4.0188 | 3.9437
94.31 | 94.45 |  | 14 | 6.35 | 1345 | 919 | 443.3687 | 3.0336 | 3.1573
129.6 | 129.72 |  | 12 | 6.35 | 992 | 626 | 380.0303 | 2.6103 | 2.7104
151.18 | 151.33 |  | 15 | 6.35 | 1671 | 1205 | 475.0379 | 3.5176 | 3.5858
154.955 | 155.08 |  | 12.5 | 6.35 | 1281 | 873 | 395.8649 | 3.236 | 3.1397
169.23 | 169.33 |  | 10 | 6.35 | 900 | 603 | 316.6919 | 2.8419 | 3.0303
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!

## Logging - Lithology (L)
From (m) | To (m) | Interval (m) | Recovery (m) | Unit Code | Unit | Sulphide Units | Description
0 | 12 | 12 |  |  |  |  | Casing - No recovery
12 | 21 | 9 |  |  | Overburden |  | OVB
21 | 24 | 3 |  |  | N/A |  | poorly mixed bedrock phyllite. Not includled in log because of unreliability
24 | 30 | 6 |  | 5B0 | Vangorda FM
30 | 32 | 2 |  | 5B8 | Vangorda FM
32 | 33 | 1 |  | 5B0 | Vangorda FM
33 | 34 | 1 |  | 5B8 | Vangorda FM
34 | 34.48 | 0.48 |  | 5B0 | Vangorda FM
34.48 | 36 | 1.52 |  | 5B8Q | Vangorda FM |  | Chloritic phyllite with quartz veining up to 8 cm
36 | 38.64 | 2.64 |  | 5B0Q | Vangorda FM | Pyrite (2%) | Fracture quartz veining up to 80 cm (37.84-38.64m) hosting pyrite
38.64 | 39.5 | 0.86 |  | F | Fault |  | Intensely broken down graphitic phyllite
39.5 | 54 | 14.5 |  | 5G0R | Vangorda FM | Pyrite (1%) | Rare disseminated pyrite
54 | 57 | 3 |  | 5D0Q | Vangorda FM | Pyrite (2%) | Intermittent quart-carbonate veining present. Beige laminar strata present
57 | 70.55 | 13.55 |  | 5G0(Q) | Vangorda FM | Pyrite (1%) | Chloritic quartz vein hosting disseminated pyrite 59.78-60.41m
70.55 | 71.2 | 0.65 |  | 5F9L | Vangorda FM | Sphalerite (4%), Pyrite (3%) | laminated chloritic phyllite with banded sphalerite-pyrite
71.2 | 73.1 | 1.9 |  | 4A34 | Banded Sulphides | Pyrite (10%), Sphalerite (3%)
73.1 | 81.12 | 8.02 |  | 4A34Q | Banded Sulphides | Pyrite (25%), Sphalerite (6%), Galena (3%), Chalcopyrite (2%), Pyrrhotite (?%) | Quartzite to phyllite interbeds with rare narrow quartz veins
81.12 | 85.11 | 3.99 |  | 4E4EQ | Massive Sulphides | Pyrite (60%), Sphalerite (15%), Galena (6%), Barite (2%), Chalcopyrite (2%), Pyrrhotite (?%) | Barite lense with interspersed pyrite from 84.70-84.92m
85.11 | 91.1 | 5.99 |  | 4A34 | Banded Sulphides | Pyrite (25%), Sphalerite (6%), Galena (3%), Chalcopyrite (2%), Pyrrhotite (?%) | Quartzite to phyllite interbeds
91.1 | 92.53 | 1.43 |  | 4E4E | Massive Sulphides | Pyrite (60%), Sphalerite (10%), Galena (7%), Barite (10%), Chalcopyrite (2%), Pyrrhotite (?%) | Quartz and barite present from 92-92.24
92.53 | 94.55 | 2.02 |  | 4A34 | Banded Sulphides | Pyrite (25%), Sphalerite (6%), Galena (3%), Chalcopyrite (2%), Pyrrhotite (?%) | Quartzite to phyllite interbeds
94.55 | 96.47 | 1.92 |  | 4A34 | Banded Sulphides | Pyrite (10%), Sphalerite (5) | Banded to massive pyritic sulphides +- sphalerite with narrow horizon of chloritic laminar phyllite (5D8) from 94.55-94.80m
96.47 | 97.68 | 1.21 |  | 4E4E | Massive Sulphides | Pyrite (60%), Sphalerite (15%), Galena (6%), Chalcopyrite (2%), Pyrrhotite (?%)
97.68 | 99.84 | 2.16 |  | 5D8E | Vangorda FM | Pyrite (5%), Sphalerite (5%) | Beige to chloritic laminar unit with chaotic lenses of sulphide and minor breccia
99.84 | 107.61 | 7.77 |  | 4A34 | Banded Sulphides | Pyrite (25%), Sphalerite (6%), Galena (3%), Chalcopyrite (2%), Pyrrhotite (?%) | Quartzite to phyllite interbeds
107.61 | 111 | 3.39 |  | 4A34 | Banded Sulphides | Pyrite (35%), Sphalerite (8%), Galena (5%), Chalcopyrite (1%), Pyrrhotite (?%) | Quartzite to phyllite interbeds
111 | 114.02 | 3.02 |  | 4E4E | Massive Sulphides | Pyrite (65%), Sphalerite (10%), Galena (7%)
114.02 | 115.3 | 1.28 |  | 5A5 | Vangorda FM
115.3 | 136.87 | 21.57 |  | 5B38 | Vangorda FM
136.87 | 140.38 | 3.51 |  | 4A4Q | Banded Sulphides | Pyrite (15%), Sphalerite (5%), Galena (5%)
140.38 | 156 | 15.62 |  | 4A4 | Banded Sulphides | Pyrite (45%), Sphalerite (7%), Galena (3%), Chalcopyrite (1-2%), Pyrrhotite (?%)
156 | 166.91 | 10.91 |  | 4H9 | Banded Sulphides | Pyrite (15%), Pyrrhotite (15%), Chalcopyrite (4%)
166.91 | 168.52 | 1.61 |  | 4H9Q | Banded Sulphides | Pyrite (15%), Pyrrhotite (15%), Chalcopyrite (4%) | 50 cm quartz vein
168.52 | 169.74 | 1.22 |  | 4H9 | Banded Sulphides | Pyrite (15%), Pyrrhotite (15%), Chalcopyrite (4%)
169.74 | 175 | 5.26 |  | 5B0Q | Vangorda FM |  | Intermittent chloritic quartz veining up to 50 cm wide.
175 | 177.1 | 2.1 |  | 5B0 | Vangorda FM
177.1 | 180 | 2.9 |  | 5BF | Fault |  | gouged fault zone at end of hole

## Logging (Alteration)
From (m) | To (m) | Interval (m) | Alteration Type | Alteration Intensity
0
0
0

## Logging - Structure (S)
From (m) | To (m) | Interval (m) | Primary Structure Type | Secondary Structure Type | Fault Features | Fault Degree | Attitude | Description
38.64 | 39.5 | 0.86 |  | Fault | R | 3 |  | Rubbly contacts
177.1 | 180 | 2.9 |  | Fault | RG | 2 | 70
1 | 1.01 | 0.01 | Bedding (S0) |  |  |  | -
2 | 2.01 | 0.01 | Bedding (S0) |  |  |  | -
3 | 3.01 | 0.01 | Bedding (S0) |  |  |  | -
4 | 4.01 | 0.01 | Bedding (S0) |  |  |  | -
5 | 5.01 | 0.01 | Bedding (S0) |  |  |  | -
6 | 6.01 | 0.01 | Bedding (S0) |  |  |  | -
7 | 7.01 | 0.01 | Bedding (S0) |  |  |  | -
8 | 8.01 | 0.01 | Bedding (S0) |  |  |  | -
9 | 9.01 | 0.01 | Bedding (S0) |  |  |  | -
10 | 10.01 | 0.01 | Bedding (S0) |  |  |  | -
11 | 11.01 | 0.01 | Bedding (S0) |  |  |  | -
12 | 12.01 | 0.01 | Bedding (S0) |  |  |  | -
13 | 13.01 | 0.01 | Bedding (S0) |  |  |  | -
14 | 14.01 | 0.01 | Bedding (S0) |  |  |  | -
15 | 15.01 | 0.01 | Bedding (S0) |  |  |  | -
16 | 16.01 | 0.01 | Bedding (S0) |  |  |  | -
17 | 17.01 | 0.01 | Bedding (S0) |  |  |  | -
18 | 18.01 | 0.01 | Bedding (S0) |  |  |  | -
19 | 19.01 | 0.01 | Bedding (S0) |  |  |  | -
20 | 20.01 | 0.01 | Bedding (S0) |  |  |  | -
21 | 21.01 | 0.01 | Bedding (S0) |  |  |  | -
22 | 22.01 | 0.01 | Bedding (S0) |  |  |  | -
23 | 23.01 | 0.01 | Bedding (S0) |  |  |  | 85
24 | 24.01 | 0.01 | Bedding (S0) |  |  |  | 85
25 | 25.01 | 0.01 | Bedding (S0) |  |  |  | 80
26 | 26.01 | 0.01 | Bedding (S0) |  |  |  | 70
27 | 27.01 | 0.01 | Bedding (S0) |  |  |  | 70
28 | 28.01 | 0.01 | Bedding (S0) |  |  |  | 60
29 | 29.01 | 0.01 | Bedding (S0) |  |  |  | 70
30 | 30.01 | 0.01 | Bedding (S0) |  |  |  | 50
31 | 31.01 | 0.01 | Bedding (S0) |  |  |  | 80
32 | 32.01 | 0.01 | Bedding (S0) |  |  |  | 75
33 | 33.01 | 0.01 | Bedding (S0) |  |  |  | 85
34 | 34.01 | 0.01 | Bedding (S0) |  |  |  | 55
35 | 35.01 | 0.01 | Bedding (S0) |  |  |  | 70
36 | 36.01 | 0.01 | Bedding (S0) |  |  |  | 75
37 | 37.01 | 0.01 | Bedding (S0) |  |  |  | 80
38 | 38.01 | 0.01 | Bedding (S0) |  |  |  | -
39 | 39.01 | 0.01 | Bedding (S0) |  |  |  | -
40 | 40.01 | 0.01 | Bedding (S0) |  |  |  | 20
41 | 41.01 | 0.01 | Bedding (S0) |  |  |  | 45
42 | 42.01 | 0.01 | Bedding (S0) |  |  |  | 60
43 | 43.01 | 0.01 | Bedding (S0) |  |  |  | 55
44 | 44.01 | 0.01 | Bedding (S0) |  |  |  | 75
45 | 45.01 | 0.01 | Bedding (S0) |  |  |  | 50
46 | 46.01 | 0.01 | Bedding (S0) |  |  |  | 60
47 | 47.01 | 0.01 | Bedding (S0) |  |  |  | 75
48 | 48.01 | 0.01 | Bedding (S0) |  |  |  | 75
49 | 49.01 | 0.01 | Bedding (S0) |  |  |  | 80
50 | 50.01 | 0.01 | Bedding (S0) |  |  |  | 75
51 | 51.01 | 0.01 | Bedding (S0) |  |  |  | 75
52 | 52.01 | 0.01 | Bedding (S0) |  |  |  | 75
53 | 53.01 | 0.01 | Bedding (S0) |  |  |  | 75
54 | 54.01 | 0.01 | Bedding (S0) |  |  |  | 75
55 | 55.01 | 0.01 | Bedding (S0) |  |  |  | 70
56 | 56.01 | 0.01 | Bedding (S0) |  |  |  | 75
57 | 57.01 | 0.01 | Bedding (S0) |  |  |  | 70
58 | 58.01 | 0.01 | Bedding (S0) |  |  |  | 70
59 | 59.01 | 0.01 | Bedding (S0) |  |  |  | 70
60 | 60.01 | 0.01 | Bedding (S0) |  |  |  | 80
61 | 61.01 | 0.01 | Bedding (S0) |  |  |  | 80
62 | 62.01 | 0.01 | Bedding (S0) |  |  |  | 80
63 | 63.01 | 0.01 | Bedding (S0) |  |  |  | 90
64 | 64.01 | 0.01 | Bedding (S0) |  |  |  | 80
65 | 65.01 | 0.01 | Bedding (S0) |  |  |  | 75
66 | 66.01 | 0.01 | Bedding (S0) |  |  |  | 85
67 | 67.01 | 0.01 | Bedding (S0) |  |  |  | 80
68 | 68.01 | 0.01 | Bedding (S0) |  |  |  | 80
69 | 69.01 | 0.01 | Bedding (S0) |  |  |  | 80
70 | 70.01 | 0.01 | Bedding (S0) |  |  |  | 85
71 | 71.01 | 0.01 | Bedding (S0) |  |  |  | 75
72 | 72.01 | 0.01 | Bedding (S0) |  |  |  | 80
73 | 73.01 | 0.01 | Bedding (S0) |  |  |  | 80
74 | 74.01 | 0.01 | Bedding (S0) |  |  |  | -
75 | 75.01 | 0.01 | Bedding (S0) |  |  |  | 70
76 | 76.01 | 0.01 | Bedding (S0) |  |  |  | 80
77 | 77.01 | 0.01 | Bedding (S0) |  |  |  | -
78 | 78.01 | 0.01 | Bedding (S0) |  |  |  | 70
79 | 79.01 | 0.01 | Bedding (S0) |  |  |  | 70
80 | 80.01 | 0.01 | Bedding (S0) |  |  |  | 80
81 | 81.01 | 0.01 | Bedding (S0) |  |  |  | 80
82 | 82.01 | 0.01 | Bedding (S0) |  |  |  | 80
83 | 83.01 | 0.01 | Bedding (S0) |  |  |  | 65
84 | 84.01 | 0.01 | Bedding (S0) |  |  |  | 70
85 | 85.01 | 0.01 | Bedding (S0) |  |  |  | 80
86 | 86.01 | 0.01 | Bedding (S0) |  |  |  | 60
87 | 87.01 | 0.01 | Bedding (S0) |  |  |  | -
88 | 88.01 | 0.01 | Bedding (S0) |  |  |  | 70
89 | 89.01 | 0.01 | Bedding (S0) |  |  |  | -
90 | 90.01 | 0.01 | Bedding (S0) |  |  |  | -
91 | 91.01 | 0.01 | Bedding (S0) |  |  |  | 80
92 | 92.01 | 0.01 | Bedding (S0) |  |  |  | 60
93 | 93.01 | 0.01 | Bedding (S0) |  |  |  | 80
94 | 94.01 | 0.01 | Bedding (S0) |  |  |  | 50
95 | 95.01 | 0.01 | Bedding (S0) |  |  |  | 50
96 | 96.01 | 0.01 | Bedding (S0) |  |  |  | -
97 | 97.01 | 0.01 | Bedding (S0) |  |  |  | 70
98 | 98.01 | 0.01 | Bedding (S0) |  |  |  | 70
99 | 99.01 | 0.01 | Bedding (S0) |  |  |  | 75
100 | 100.01 | 0.01 | Bedding (S0) |  |  |  | 80
101 | 101.01 | 0.01 | Bedding (S0) |  |  |  | 70
102 | 102.01 | 0.01 | Bedding (S0) |  |  |  | 70
103 | 103.01 | 0.01 | Bedding (S0) |  |  |  | 60
104 | 104.01 | 0.01 | Bedding (S0) |  |  |  | 75
105 | 105.01 | 0.01 | Bedding (S0) |  |  |  | 70
106 | 106.01 | 0.01 | Bedding (S0) |  |  |  | 70
107 | 107.01 | 0.01 | Bedding (S0) |  |  |  | 75
108 | 108.01 | 0.01 | Bedding (S0) |  |  |  | 65
109 | 109.01 | 0.01 | Bedding (S0) |  |  |  | 65
110 | 110.01 | 0.01 | Bedding (S0)
111 | 111.01 | 0.01 | Bedding (S0) |  |  |  | 70
112 | 112.01 | 0.01 | Bedding (S0)
113 | 113.01 | 0.01 | Bedding (S0) |  |  |  | 60
114 | 114.01 | 0.01 | Bedding (S0) |  |  |  | 70
115 | 115.01 | 0.01 | Bedding (S0) |  |  |  | -
116 | 116.01 | 0.01 | Bedding (S0) |  |  |  | -
117 | 117.01 | 0.01 | Bedding (S0) |  |  |  | 80
118 | 118.01 | 0.01 | Bedding (S0) |  |  |  | 75
119 | 119.01 | 0.01 | Bedding (S0) |  |  |  | 75
120 | 120.01 | 0.01 | Bedding (S0) |  |  |  | 85
121 | 121.01 | 0.01 | Bedding (S0) |  |  |  | 85
122 | 122.01 | 0.01 | Bedding (S0) |  |  |  | 85
123 | 123.01 | 0.01 | Bedding (S0) |  |  |  | 80
124 | 124.01 | 0.01 | Bedding (S0) |  |  |  | 80
125 | 125.01 | 0.01 | Bedding (S0) |  |  |  | 80
126 | 126.01 | 0.01 | Bedding (S0) |  |  |  | 85
127 | 127.01 | 0.01 | Bedding (S0) |  |  |  | 85
128 | 128.01 | 0.01 | Bedding (S0) |  |  |  | 85
129 | 129.01 | 0.01 | Bedding (S0) |  |  |  | 85
130 | 130.01 | 0.01 | Bedding (S0) |  |  |  | 85
131 | 131.01 | 0.01 | Bedding (S0) |  |  |  | 85
132 | 132.01 | 0.01 | Bedding (S0) |  |  |  | 85
133 | 133.01 | 0.01 | Bedding (S0) |  |  |  | 85
134 | 134.01 | 0.01 | Bedding (S0) |  |  |  | 85
135 | 135.01 | 0.01 | Bedding (S0) |  |  |  | 75
136 | 136.01 | 0.01 | Bedding (S0) |  |  |  | 85
137 | 137.01 | 0.01 | Bedding (S0) |  |  |  | 80
138 | 138.01 | 0.01 | Bedding (S0) |  |  |  | 80
139 | 139.01 | 0.01 | Bedding (S0) |  |  |  | 80
140 | 140.01 | 0.01 | Bedding (S0) |  |  |  | 80
141 | 141.01 | 0.01 | Bedding (S0) |  |  |  | 75
142 | 142.01 | 0.01 | Bedding (S0) |  |  |  | 80
143 | 143.01 | 0.01 | Bedding (S0) |  |  |  | 70
144 | 144.01 | 0.01 | Bedding (S0) |  |  |  | 80
145 | 145.01 | 0.01 | Bedding (S0) |  |  |  | 80
146 | 146.01 | 0.01 | Bedding (S0) |  |  |  | 80
147 | 147.01 | 0.01 | Bedding (S0) |  |  |  | 85
148 | 148.01 | 0.01 | Bedding (S0) |  |  |  | 80
149 | 149.01 | 0.01 | Bedding (S0) |  |  |  | 85
150 | 150.01 | 0.01 | Bedding (S0) |  |  |  | 80
151 | 151.01 | 0.01 | Bedding (S0) |  |  |  | 70
152 | 152.01 | 0.01 | Bedding (S0) |  |  |  | 70
153 | 153.01 | 0.01 | Bedding (S0) |  |  |  | 65
154 | 154.01 | 0.01 | Bedding (S0) |  |  |  | 75
155 | 155.01 | 0.01 | Bedding (S0) |  |  |  | 75
156 | 156.01 | 0.01 | Bedding (S0) |  |  |  | 70
157 | 157.01 | 0.01 | Bedding (S0) |  |  |  | 75
158 | 158.01 | 0.01 | Bedding (S0) |  |  |  | 80
159 | 159.01 | 0.01 | Bedding (S0) |  |  |  | 75
160 | 160.01 | 0.01 | Bedding (S0) |  |  |  | 75
161 | 161.01 | 0.01 | Bedding (S0) |  |  |  | 75
162 | 162.01 | 0.01 | Bedding (S0) |  |  |  | 75
163 | 163.01 | 0.01 | Bedding (S0) |  |  |  | 70
164 | 164.01 | 0.01 | Bedding (S0) |  |  |  | 70
165 | 165.01 | 0.01 | Bedding (S0) |  |  |  | 70
166 | 166.01 | 0.01 | Bedding (S0) |  |  |  | 70
167 | 167.01 | 0.01 | Bedding (S0) |  |  |  | 65
168 | 168.01 | 0.01 | Bedding (S0) |  |  |  | 65
169 | 169.01 | 0.01 | Bedding (S0) |  |  |  | 75
170 | 170.01 | 0.01 | Bedding (S0) |  |  |  | 70
171 | 171.01 | 0.01 | Bedding (S0) |  |  |  | 75
172 | 172.01 | 0.01 | Bedding (S0) |  |  |  | 75
173 | 173.01 | 0.01 | Bedding (S0) |  |  |  | 65
174 | 174.01 | 0.01 | Bedding (S0) |  |  |  | 70
175 | 175.01 | 0.01 | Bedding (S0) |  |  |  | 70
176 | 176.01 | 0.01 | Bedding (S0) |  |  |  | 70
177 | 177.01 | 0.01 | Bedding (S0) |  |  |  | 65
178 | 178.01 | 0.01 | Bedding (S0) |  |  |  | 60
179 | 179.01 | 0.01 | Bedding (S0) |  |  |  | 60
180 | 180.01 | 0.01 | Bedding (S0) |  |  |  | 60

## Sampling (P)
From (m) | To (m) | Interval (m) | Sample Number | QA / QC | Batch | Security Tag | Comment
0 | 12 | 12 |  |  |  |  | Casing, no recovery and OVB
12 | 22 | 10 |  |  |  |  | OVB
22 | 24 | 2 |  |  |  |  | Unreliably broken - not sampled
24 | 26 | 1.46 | D938682 |  | 22-024
26 | 28 | 1.34 | D938683 |  | 22-024
28 | 30 | 1.53 | D938684 |  | 22-024
28 | 30 | 1.53 | D938685 | Coarse Reject Duplicate | 22-024
30 | 32 | 1.53 | D938686 |  | 22-024
32 | 34 | 1.44 | D938687 |  | 22-024
34 | 36 | 1.85 | D938688 |  | 22-024
36 | 37.84 | 1.75 | D938689 |  | 22-024
- | - | - | D938690 | Standard - CDN ME-1601 | 22-024
37.84 | 38.64 | 1.21 | D938691 |  | 22-024
38.64 | 40 | 1.31 | D938692 |  | 22-024
40 | 42 | 1.81 | D938693 |  | 22-024
42 | 44 | 1.89 | D938694 |  | 22-024
44 | 46 | 1.74 | D938695 |  | 22-024
46 | 48 | 1.88 | D938696 |  | 22-024
48 | 50 | 1.91 | D938697 |  | 22-024
48 | 50 | 1.91 | D938698 | Coarse Reject Duplicate | 22-024
50 | 52 | 1.69 | D938699 |  | 22-024
52 | 54 | 2 | D938700 |  | 22-024
54 | 55.12 | 0.77 | D938701 |  | 22-024
55.12 | 57 | 1.6 | D938702 |  | 22-024
57 | 59 | 1.33 | D938703 |  | 22-024
59 | 60.57 | 1.57 | D938704 |  | 22-024
- | - | - | D938705 | Blank | 22-024
60.57 | 62.64 | 2.07 | D938706 |  | 22-024
62.64 | 64 | 1.36 | D938707 |  | 22-024
64 | 66 | 2 | D938708 |  | 22-024
66 | 68 | 2 | D938709 |  | 22-024
68 | 69.85 | 1.85 | D938710 |  | 22-024
69.85 | 70.55 | 0.7 | D938711 |  | 22-025
70.55 | 71.2 | 0.65 | D938712 |  | 22-025
71.2 | 72 | 0.8 | D938713 |  | 22-025
72 | 73.1 | 1.1 | D938714 |  | 22-025
73.1 | 75 | 1.9 | D938715 |  | 22-025
73.1 | 75 | 1.9 | D938716 | Coarse Reject Duplicate | 22-025
75 | 76.67 | 1.67 | D938717 |  | 22-025
76.67 | 77.53 | 0.86 | D938718 |  | 22-025
77.53 | 78.86 | 1.33 | D938719 |  | 22-025
78.86 | 79.78 | 0.92 | D938720 |  | 22-025
79.78 | 81.12 | 1.34 | D938721 |  | 22-025
- | - | - | D938722 | Blank | 22-025
81.12 | 83.12 | 2 | D938723 |  | 22-025
83.12 | 85.11 | 1.99 | D938724 |  | 22-025
85.11 | 86 | 0.89 | D938725 |  | 22-025
86 | 87.65 | 1.65 | D938726 |  | 22-025
87.65 | 89 | 1.35 | D938727 |  | 22-025
89 | 91 | 2 | D938728 |  | 22-025
89 | 91 | 2 | D938729 | Coarse Reject Duplicate | 22-025
91 | 92.53 | 1.53 | D938730 |  | 22-025
92.53 | 94.55 | 2.02 | D938731 |  | 22-025
94.55 | 96.47 | 1.92 | D938732 |  | 22-025
96.47 | 97.68 | 1.21 | D938733 |  | 22-025
97.68 | 98.6 | 0.92 | D938734 |  | 22-025
- | - | - | D938735 | Standard - CDN ME-1601 | 22-025
98.6 | 99.84 | 1.24 | D938736 |  | 22-025
99.84 | 101.25 | 1.41 | D938737 |  | 22-025
101.25 | 103 | 1.75 | D938738 |  | 22-025
103 | 105 | 2 | D938739 |  | 22-025
105 | 107 | 2 | D938740 |  | 22-025
107 | 107.61 | 0.61 | D938741 |  | 22-025
- | - | - | D938742 | Standard - CDN ME-1902 | 22-025
107.61 | 109.02 | 1.51 | D938743 |  | 22-025
109.02 | 111 | 1.98 | D938744 |  | 22-025
111 | 113 | 2 | D938745 |  | 22-025
113 | 114.02 | 1.02 | D938746 |  | 22-025
114.02 | 115.3 | 1.28 | D938747 |  | 22-025
115.3 | 117 | 1.7 | D938748 |  | 22-025
117 | 119 | 2 | D938749 |  | 22-025
119 | 121 | 2 | D938750 |  | 22-025
121 | 123 | 2 | D938751 |  | 22-026
123 | 125 | 2 | D938752 |  | 22-026
125 | 127 | 2 | D938753 |  | 22-026
127 | 129 | 2 | D938754 |  | 22-026
129 | 131 | 2 | D938755 |  | 22-026
131 | 133 | 2 | D938756 |  | 22-026
133 | 135 | 2 | D938757 |  | 22-026
135 | 137 | 2 | D938758 |  | 22-026
- | - | - | D938759 | Blank | 22-026
137 | 139 | 2 | D938760 |  | 22-026
139 | 140.38 | 1.38 | D938761 |  | 22-026
140.38 | 142 | 1.62 | D938762 |  | 22-026
142 | 144 | 2 | D938763 |  | 22-026
142 | 144 | 2 | D938764 | Coarse Reject Duplicate | 22-026
144 | 146 | 2 | D938765 |  | 22-026
146 | 148 | 2 | D938766 |  | 22-026
148 | 150 | 2 | D938767 |  | 22-026
150 | 152 | 2 | D938768 |  | 22-026
152 | 154 | 2 | D938769 |  | 22-026
152 | 154 |  | D938770 | Coarse Reject Duplicate | 22-026
154 | 156 | 2 | D938771 |  | 22-026
156 | 158 | 2 | D938772 |  | 22-026
158 | 160 | 2 | D938773 |  | 22-026
160 | 162 | 2 | D938774 |  | 22-026
162 | 164 | 2 | D938775 |  | 22-026
164 | 166 | 2 | D938776 |  | 22-026
- | - | - | D938777 | Standard - CDN ME-1902 | 22-026
166 | 166.91 | 0.91 | D938778 |  | 22-026
166.91 | 168.52 | 1.61 | D938779 |  | 22-026
168.52 | 169.74 | 1.22 | D938780 |  | 22-026
169.74 | 171.18 | 1.44 | D938781 |  | 22-026
171.18 | 173.21 | 2.03 | D938782 |  | 22-026
- | - | - | D938783 | Standard - CDN ME-1601 | 22-026
173.21 | 175 | 1.79 | D938784 |  | 22-026
175 | 176.36 | 1.36 | D938785 |  | 22-026
176.36 | 177.4 | 1.04 | D938786 |  | 22-026
177.4 | 180 | 2.6 | D938787 |  | 22-026